## Marketing
Workgroup	No	Milestone	Task	Billable	Deliverable
	1	Pre-Design and Prep.	Feasibility Study		Feasibility Study Report
					Case Study - Concepts and Drawings
Design Studio			Coordination Meetings with Client and Internal team	0	Design Brief Document
Design Studio			RFP and Profile Development	0
Design Studio			Develop Base Maps	0
Design Studio			Develop Preliminary Concept Plans	0
Design Studio			List of Work packages	0
Design Studio			Drawing List Preparation for all work packages	0
Design Studio			Correspondence, Phone Calls, Emails	0
Design Studio			Travel	1
Design Studio	2	Concept Design	Develop Concept alternatives	1	Sketch Design Alternatives
Design Studio			Submittals/Meetings for Approval	1	Architectural Illustrations
Design Studio			Coordination markups	1	Area Calculations
Design Studio			Coordination meetings	1	Material Palettes
Design Studio			Rework on Concept Stage	1
Design Studio			Summary Design Report for Client approval	1
Design Studio			Design Refinements after Reviews	1
Design Studio			Preferred Option Closure	1
Design Studio			Final Illustrative layout confirmation of design Intent	1
Design Studio			Correspondence, Phone Calls, Emails	1
Design Studio			Travel	1
Design Studio	3	Municipal	Regulatory Requirements Study	1	Municipal Sanction Drawings in prescribed format
Design Studio	4	Schematic Design	Schematic Architectural Drawing Set	1	Architecture design Intent Drawings
Design Studio			Schedule of Finishes	1	Floor Plans
Design Studio			Schedule of D/W, Openings and Glazing	1	Exterior Elevations
Design Studio			Detailed Design of Areas	1	Conceptual Sections
Design Studio			Spot Details Sheet development	1
Design Studio			Site Plan Development	1
Design Studio			Review Palette of Building and Landscape Materials and Colors	1
Design Studio			Landscape Standards (Parks, Gardens, Courts and Plazas)	1
Design Studio			Develop a Landscape Framework Report (Draft) Plan & Text	1
Design Studio			Recommend Energy Conservation Measures	1
Design Studio			Develop Final Lighting Plan	1
Design Studio			Landscape Consultant Coordination	1
Design Studio			Rework / Abortive Works	1
Design Studio			Additional works not scoped	1
Design Studio			Structural Coordination	1
Design Studio			MEP Coordination Drawings	1
Design Studio			Shop Drgs Dev coordination	1
Design Studio			3D Presentation/Perspective Views, Models /Sims	1
Design Studio			Project Documentation, Estimation and Correspondence	1
Design Studio			Coordination with Approval Authorities during construction	1
Design Studio			Review/Approval meetings as reqd during process	1
Design Studio			Coordination markups	1
Design Studio			Coordination meetings	1
Design Studio			Correspondence, Phone Calls, Emails	1
Design Studio			Travel	1
Design Studio	5	Design Development	Detailed Architectural Drawing Set	1	Structure, MEP drawing development based on the Architecture Intent Drawing Set
Design Studio			Schedule of Finishes	1	Schematic single-line diagrams of all services
Design Studio			Schedule of D/W, Openings and Glazing	1	Drawings with services drawn on floor plans and sections
Design Studio			Detailed Design of Areas	1
Design Studio			Spot Details Sheet development	1
Design Studio			Site Plan Development	1
Design Studio			Landscape Consultant Coordination	1
Design Studio			Rework / Abortive Works	1
Design Studio			Additional works not scoped	1
Design Studio			Structural Coordination	1
Design Studio			MEP Coordination Drawings	1
Design Studio			Shop Drgs Dev coordination	1
Design Studio			List of Work Packages	1
Design Studio			Internal Review Meeting with Team	1
Design Studio			Review Meeting with CLIENT and Team	1
Design Studio			Prepare Final Arch Drawings for MEP/Structure sendout	1
Design Studio			Submittals for Approval	1
Design Studio			Coordination External Consultants/ Markups/Meetings	1
Design Studio			Additional works not scoped	1
Design Studio			3D Presentation/Simulation, Perspective Views, Models	1
Design Studio			Correspondence, Phone Calls, Emails	1
Design Studio			Travel	1
Design Studio			Prepare Drawings/Documents Submittal for Municipal Approval	1
Design Studio			Fire Approval documents and drawings	1
Design Studio			EIA Approval documentation	1
Design Studio			Submit to CLIENT for Approval from concerned authority	1
Design Studio			Sundry Approval Meetings as required	1
Design Studio			Revisions	1
Design Studio			Correspondence, Phone Calls, Emails	1
Design Studio			Travel	1
					All Floor Plans, Terrace, Mumty detail drawings
					Elevations
					Sections
					Wall Sections
					Door, Window details
					Wet Area details
Design Studio	6	Bid Documents	Prepare Detailed Interior and Exterior Drawings	1	Tender Drawings and Techno-commercial document set
Design Studio			Develop Tender Drawing Sets	1
Design Studio			Prepare Project Implementation schedule	1
Design Studio			Prepare Tender Documents	1
Design Studio			Review Meeting with Client and Team	1
Design Studio			Tender Floating and Scrutiny	1
Design Studio			Assistance with Pre Contract Meeting/Negotiation	1
Design Studio			Submittals/Meetings for Approval	1
Design Studio			Coordination markup drawings	1
Design Studio			Coordination meetings	1
Design Studio			Project Documentation	1
Design Studio			Correspondence, Phone Calls, Emails	1
Design Studio			Travel	1
					All Floor Plans, Terrace, Mumty detail drawings
					Elevations
					Sections
					Wall Sections
					Door, Window details
					Finishes Schedule
Design Studio	7	Construction Documents	Internal Team Review and Coordination	1	Coordinated Architecture, Structure, MEP drawing set good for construction drawings
Design Studio			Prepare Detailed Interior and Exterior Drawings	1	All Floor Plans, Terrace, Mumty detail drawings
Design Studio			Preparing Coordinated GFC Architectural Drawings	1	Elevations
Design Studio			Preparing Coordinated GFC Structural Drawings	1	Sections
Design Studio			Preparing Coordinated GFC MEP Drawings	1	Wall Sections
Design Studio			Detailed Design and Spot details	1	Door, Window details
Design Studio			Design of Material palletes	1	Wet Area details
					Finishes Schedule
Design Studio			Vendor Coordination Markups,Phone calls Meetings	1	Construction details
Design Studio			Additional works not scoped	1
Design Studio			Site Supervisory Attendance, Visits & Site Meetings	1
Design Studio			Submittal work	1
Design Studio			Client Meetings for Approval	1
Design Studio			Consultant Coordination markups,meetings phone Calls	1
Design Studio			3D Presentation/Simulation, Perspective Views, Models	1
Design Studio			Rework / Abortive Works	1
Design Studio			Correspondence, Phone Calls, Emails	1
Design Studio			Travel	1
Design Studio			Mobilization and Site take-over	1
Design Studio			Correspondence, Phone Calls, Emails	1
Design Studio			Travel	1
	8	Construction Management			Periodic visit on site to review work progress is as per design intent
Design Studio	9	Project Closure	Graphics Development	1	As built drawing set
Design Studio			Prepare As built Drawings/Coordination for Services Manuals	1
Design Studio			Refinements and Rework	1
Design Studio			Report generation	1
Design Studio			Photo shoot	1
Design Studio			Correspondence, Phone Calls, Emails	1
Design Studio			Travel	1
Design Studio				1